## Meeting
PROGRESS REPORT OF CENTRAL ROAD INFRASTRUCTURE FUND
Rs in lacs
S.No | Name of work | District | Sanctioned cost | Project sanctioned in FY | Cumm Expdt March 2020 | Funds released 2020-21 | %age
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Impvt./ Upgd of R S Pura to Chakroi | Jammu | 111.02 | 2000-01 | 111.02 | 0 | 100
2 | Const. of approach of Multi cell Box over Landoi Choi Nallah of Nanak Nagar Jammu | Jammu | 71.34 | 2000-01 | 71.24 | 0 | 100
3 | Compl. Of 2nd bridge over River Tawi 299m | Jammu | 427 | 2000-01 | 422 | 0 | 100
4 | Const. of 3rd Tawi bridge at Jammu | Jammu | 580 | 2000-01 | 580 | 0 | 100
5 | Impvt/ Upgad of road Hotel Asia to M.G. chowk Satwari | Jammu | 108 | 2000-01 | 108 | 0 | 100
6 | Impvt/ Upgad of Biaspur Parlah | Jammu | 22.85 | 2000-01 | 22.85 | 0 | 100
7 | Const. of 100 Mt span vented cause way Garore Nallah Biaspur Parlah road | Jammu | 78.54 | 2000-01 | 78.54 | 0 | 100
8 | Impvt/ Upgad of road from R. S Pura to Old Agra Chak | Jammu | 61.15 | 2000-01 | 61.15 | 0 | 100
9 | Upgd of Patnitop Sansar road Km 1st to 10th | Ramban | 302 | 2000-01 | 297 | 0 | 100
10 | Widening of Srinagar Baramulla Batmaloo Qamarwari (six lane) | Srinagar | 1173.4 | 2000-01 | 1173.4 | 0 | 100
11 | Srinagar Harwan road by way of providing nenawal coat and improve the foot path (2 lane) | Srinagar | 247 | 2000-01 | 247 | 0 | 100
12 | Const. of Nowpora bridge Sgr Sonmarg road | Srinagar | 182.32 | 2000-01 | 182.32 | 0 | 100
13 | Const. of 230 Mtr steel Bridge Nallah Bheeni at Ladhnoo Billawar | Kathua | 791.81 | 2001-02 | 861.81 | 0 | 100
14 | Const. of Bani Daggar road | Kathua | 238.2 | 2001-02 | 248.2 | 0 | 100
15 | Imvt./ upgd of Lakhanpur thin road Km 1st to 21st | Kathua | 203.88 | 2001-02 | 213.88 | 0 | 100
16 | Const. of Dual carriage from Hazratbal Adha to Habak Crossing (4 lanes) | Srinagar | 344.7 | 2001-02 | 344.7 | 0 | 100
17 | Dual Carrageway from Nageen to Hazratbal Adda (2 lane) | Srinagar | 312.38 | 2001-02 | 312.38 | 0 | 100
18 | Dual Carrageway from Saidakadal to Nageen (2 lane) | Srinagar | 369.86 | 2001-02 | 369.86 | 0 | 100
19 | Dual Carrageway from Rainawari to Saidakadal (2 lane) | Srinagar | 331.97 | 2001-02 | 331.97 | 0 | 100
20 | Dual Carrageway from Khokhan Rainawari in Sgr City (2 lane) | Srinagar | 362.74 | 2001-02 | 362.74 | 0 | 100
21 | Dual Carrageway from Dalgate to Khokhan (2 lane) | Srinagar | 353.84 | 2001-02 | 353.84 | 0 | 100
22 | Dual Carrageway from Habak to Zukara | Srinagar | 218.48 | 2001-02 | 218.48 | 0 | 100
23 | Rehd of 79. 20 Mtr span bridge at Jaganoo over river Tawi | Udhampur | 100 | 2001-02 | 90 | 0 | 100
24 | Impvt/ Upgd of Udhampur Ghordi road Km 17 to 38 | Udhampur | 594.4 | 2001-02 | 653.4 | 0 | 100
25 | Upgd/ Impv of Dablair Sai road in Jammu | Jammu | 123.89 | 2003-04 | 123.89 | 0 | 100
26 | Circular road Jammu (Panjthriti to Sidhra) | Jammu | 137.05 | 2003-04 | 137 | 0 | 100
27 | Upgd/ Rajbagh Hera chak road in Kathua | Kathua | 79.62 | 2003-04 | 79.62 | 0 | 100
28 | Impvt of Makhar kote Ukhral road | Ramban | 96.57 | 2003-04 | 91.57 | 0 | 100
29 | Imvt of Tikri Katra road Katra town to Panthal (Udhampur) | Reasi | 363.15 | 2003-04 | 399.46 | 0 | 100
30 | Const. of addl.2 lane bridge Ashai bagh Sgr- Sonmarg road. | Srinagar | 229 | 2003-04 | 229 | 0 | 100
31 | Const. of Addl.2 lane bridge Saidakadal | Srinagar | 99 | 2003-04 | 99 | 0 | 100
32 | Const. of 2 lane bridge Dalgate | Srinagar | 310 | 2003-04 | 310 | 0 | 100
33 | Imvt./ Upgrd.of I.G road Const. of deep drain | Srinagar | 930 | 2003-04 | 930 | 0 | 100
34 | Dev. of North South Corriodore Phase I (Soura to Pandach) | Srinagar | 486 | 2003-04 | 486 | 0 | 100
35 | Imvt/ of Keller Domail road Udhampur | Udhampur | 173 | 2003-04 | 138 | 0 | 100
36 | Const. of Rangasangam Amarnath Holi Cave | Ganderbal | 1997.39 | 2004-05 | 250.5 | 0 | 10
37 | Const./ Upgd of Verinag Kokernag road via Batagund | Anantnag | 700 | 2005-06 | 700 | 0 | 100
38 | Upgd./ of Pahalgam Chandenwari road | Anantnag | 406.96 | 2005-06 | 406.96 | 0 | 100
39 | Upgd of Doda Dessa road revised | Doda | 518 | 2005-06 | 518 | 0 | 100
40 | Imvt of Thatri Kilotra 1- 18 | Doda | 1807.38 | 2005-06 | 1988.12 | 0 | 100
41 | Thathri Kilotran Km 19-40 | Doda | 2099.91 | 2005-06 | 2309.09 | 0 | 95
42 | Upgd./ Widening of Janipur to Amgrota road 7 to 24 km | Jammu | 728.5 | 2005-06 | 728.5 | 0 | 100
43 | Double lane Satwari Airport ot R. S Pura Ballol Nallah | Jammu | 1146 | 2005-06 | 1256 | 0 | 100
44 | Imvt of Tikri Katra road Km 1 to 5 Vaishno Devi side | Reasi | 371 | 2005-06 | 408.1 | 0 | 100
45 | Dev. of North South Corriodor Phase II (Pandach to Soura Ph II) | Srinagar | 684.12 | 2005-06 | 684.12 | 0 | 100
46 | Imvt./ Upgd Northern Foreshore road Nishat to Naseem Bagh | Srinagar | 609 | 2005-06 | 609 | 0 | 100
47 | Const.of Changa Kahal Jugalssar | Doda | 2525 | 2006-07 | 2507.42 | 17.58 | 95
48 | Const. of Gandoh -Jai road via Sinoo | Doda | 2710 | 2006-07 | 2641.29 | 68.71 | 95
49 | Improvement/upgradation and construction of Mandi Phagla Buffliaz road | Poonch | 4281.52 | 2006-07 | 4178.46 | 0 | 90
50 | Upgrd. of Verinag Feeder Road in Distt. Anantnag in J&K | Anantnag | 439 | 2007-08 | 439 | 0 | 100
51 | Widening/Upgrd of Bugroo Khan Saheb Dood Pathri road in J&K | Budgam | 1997 | 2007-08 | 2195.35 | 0 | 100
52 | Cons.of road from Kahara Jai Road up to village Jaura in Doda District | Doda | 2078 | 2007-08 | 2078 | 0 | 93
53 | Constof 414.70m Span (14x26m and 2x25.35m) Steel Girder Bridge over Manowa Tawi Kathar Tehsil Akhnoor in Jammu Distt. Of J&K. | Jammu | 1844 | 2007-08 | 1815 | 0 | 100
54 | Const. of 137.00 m central Span + 2x250.00 m end balanced cantilever PSC Bridge over Chenab at Meri Mendraiya in Akhnoor Distt of J&K | Jammu | 2182 | 2007-08 | 2146 | 0 | 100
55 | Widening/Upgrd Treva- Pindi Kathar road in J&K | Jammu | 570 | 2007-08 | 620 | 0 | 100
56 | Const. of 311.00 m Span (10x26 & 2x25.50) Steel Girder Bridge over Bagh Nallha at Mukandpur in Distt. Kathua in J&K | Kathua | 1246 | 2007-08 | 1078.1 | 0 | 100
57 | Improvement/Upgrd. of Thanamandi Shahdra Sharief Road in Rajouri Distt of J&K | Rajouri | 743 | 2007-08 | 816.94 | 0 | 100
58 | Const. of 313.00m Span PSC Girder Bridge over Nowshera Tawi in Rajouri Distt. Of J&K. | Rajouri | 1490 | 2007-08 | 1584.5 | 0 | 100
59 | Impvt./Upgrd of Gurah Utter Road including Vented Causeway over Devak Nallah in Jammu Distt of J&K | Samba | 432 | 2007-08 | 432 | 0 | 100
60 | Impvtt./ Upgd of Kaluchak Purmandal road from Km 1.00 to Km 16.00 in J&K | Samba | 596 | 2007-08 | 596 | 0 | 100
61 | Improvement and upgradation of road from Km 1st to 5.25 and construction of road from Km 5.25 to Bhatyas Manoo road via Chilli | Doda | 3063.56 | 2008-09 | 2124.01 | 225.78 | 60
62 | Construction of 90 m span deck type steel truss girder motorable bridges over river Chenab at Thatri | Doda | 1068.18 | 2008-09 | 1068.18 | 0 | 100
63 | Construction of 58 m span motorable steel grider bridge over Kagoni Nallah to Chopan Gungoh | Doda | 261.82 | 2008-09 | 288.02 | 0 | 100
64 | Construction of road from Bhella to Rokali via Panshai Km 9th to Km 17th including upgradation from Km 1st to km 17th | Doda | 903.53 | 2008-09 | 903.53 | 0 | 97
65 | Construction of road from Malnai to Chakabati Km 1st to Km 10th | Doda | 691.2 | 2008-09 | 760.32 | 0 | 98
66 | Construction of road from Bhalla to Trown via Shangroo from Km 8th to Km 12th including upgradation of the road from Km 1st to Km 12th | Doda | 576.4 | 2008-09 | 634.04 | 0 | 100
67 | Construction of road from Bhalla to Tesna Km 1st to Km 10th | Doda | 783.29 | 2008-09 | 861.61 | 0 | 95
68 | Construction of road from Gajoth to Dugli including widening of first 3.2 kms of Bhalla Malothi road | Doda | 540.42 | 2008-09 | 594.46 | 0 | 98
69 | Construction of road from Kulgam to chamgund | Kulgam | 746.45 | 2008-09 | 746.45 | 0 | 100
70 | Const of 152 mt 4x38 mtrs span double lane pre stressed concrete girder bridge and right / left approaches at Muradpur (District Rajouri) | Rajouri | 828.03 | 2008-09 | 888 | 0 | 100
71 | Construction of 195 mt span double lane bridge over Jhajjar Nallah with approaches to connect SMVD University / cancer hospital | Reasi | 1620.1 | 2008-09 | 1782.1 | 0 | 100
72 | Improvement/upgradation of road from Khanyar Qamarwari Gojwara (Nallah Maar) road including Additional Bridge over river Jehlum | Srinagar | 1585.72 | 2008-09 | 1655.72 | 0 | 95
73 | Widening of Maulana Azad Road from Budshah Bridge to MA Bridge | Srinagar | 1064 | 2008-09 | 1064 | 0 | 100
74 | Widening of road from Police Control Room to Batmaloo bridge | Srinagar | 362.9 | 2008-09 | 362.9 | 0 | 100
75 | Improvement/upgradation of Baghi Ali Mardan Khan Hazratbal road | Srinagar | 612.97 | 2008-09 | 612.97 | 0 | 100
76 | Improvement / strengthening of existing road of Khanyar Zadibal Pandach (KZP) | Srinagar | 305.58 | 2008-09 | 305.58 | 0 | 100
77 | Const / upgrad of Bonyar Trikanjan Maidanan road | Baramulla | 461.61 | 2009-10 | 461.61 | 0 | 100
78 | Const of road from Warapora to Fruit Mandi via Saidpora and Model Town Sopore | Baramulla | 1881.98 | 2009-10 | 1821.5 | 0 | 100
79 | Impvt / upgrad of Beehama Safapora road | Ganderbal | 1556.81 | 2009-10 | 1544.86 | 8.55 | 100
80 | Upgradation / widening of Bantalab Barnai road | Jammu | 393.4 | 2009-10 | 423.4 | 0 | 100
81 | Impvt & Upgrad of Dunadi Bunjwah link road from Km 1st to 13th | Kishtwar | 1147.52 | 2009-10 | 1137.92 | 0 | 85
82 | Impvt & Upgrd of Kurya Keshwan road Km 1st to Km 10th | Kishtwar | 1530.51 | 2009-10 | 1475.17 | 55.34 | 94
83 | Const & upgrad Singhpora to Singhpora Tunnel point Km 1st to 6th | Kishtwar | 868.71 | 2009-10 | 863.83 | 4.88 | 100
84 | Widening of National Highway from Qamerwari chowk to Parimpora / Bypass junction as four lane | Srinagar | 1379.39 | 2009-10 | 1379.39 | 0 | 100
85 | Construction of Khanabal Junction - Mehandi Kadal road | Anantnag | 466 | 2010-11 | 442.96 | 0 | 95
86 | Construction of Ladoora Jahama Bridge over river Jehlum | Baramulla | 1087 | 2010-11 | 1087 | 0 | 100
87 | Construction of Bhalessa Bhasderwah Road from village Amar - Khanitop via Bhall Padri road. | Doda | 1022 | 2010-11 | 371.91 | 0 | 35
88 | Four lanning of Satwari to Kunjwani road | Jammu | 1949 | 2010-11 | 2139 | 0 | 100
89 | Widening and Upgradation of four lanning of Satwari Airport RS Pura Road | Jammu | 1050 | 2010-11 | 1155 | 0 | 100
90 | Construction of Hasti Sarthal Deviji Road upto village Agral | Kishtwar | 1504 | 2010-11 | 1470.23 | 0.77 | 100
91 | Widening & upgradation of Tikri - Katra road | Reasi | 978 | 2010-11 | 978 | 0 | 100
92 | Construction of approach road Railway Station Katra via SMVDU | Reasi | 1591 | 2010-11 | 1591 | 0 | 100
93 | Construction of Bridge over River Jehlum at Malroo | Srinagar | 1513 | 2010-11 | 1513 | 0 | 100
94 | Construction of Zero Bridge on River Jehlum | Srinagar | 1130 | 2010-11 | 1130 | 0 | 100
95 | Construction of New Bridge over River Jhelum at Zainakadal Bridge location, Srinagar | Srinagar | 831 | 2010-11 | 831 | 0 | 100
96 | Upgrad of Lasser Yarbugh Soin Sadnara road | Baramulla | 605.75 | 2012-13 | 530.08 | 14.41 | 100
97 | Const of Gandoh Jai road (Balance portion) | Doda | 950 | 2012-13 | 434.02 | 286.6 | 85
98 | 4 lanning of Satwari Kunjwani road | Jammu | 1337 | 2012-13 | 1465 | 0 | 100
99 | Const of link road from Tatani to Bhangar in Km 1 to Km 20 | Kishtwar | 998 | 2012-13 | 30 | 0 | 0
100 | Upgrad of road from National Highway at Sangam to Industrial Growth Center Lassipora | Pulwama | 750 | 2012-13 | 750 | 0 | 100
101 | Doda Behli Lal Draman road | Doda | 803 | 2013-14 | 113.75 | 71.66 | 50
102 | Const & upgradation of Bharat Keshwan road | Doda | 1790 | 2013-14 | 0 | 0 | 6
103 | Impvt and upgradation of Nagri road to Double lane status Km 1-4 | Doda | 813 | 2013-14 | 502.88 | 59.94 | 76
104 | Const of 4x37 m intermediate lane arch type bridge at Watal Bagh Bobsipora | Ganderbal | 1556 | 2013-14 | 1425.57 | 93.2 | 94
105 | Impvt / Upgradation of link road from Chowki Choura to Katharvia Gehore | Jammu | 877.8 | 2013-14 | 845.2 | 30.88 | 100
106 | Satwari Kunjwani road Phase III | Jammu | 1600 | 2013-14 | 1488.61 | 111.39 | 100
107 | Widening & upgradation of four lanning of Satwari R S Pura road Phase III | Jammu | 2272 | 2013-14 | 1098.43 | 0 | 60
108 | Const of Buffliaz Marrah road | Poonch | 1355 | 2013-14 | 485.95 | 0 | 35
109 | Upgradation of Larkipora Zaldoora Lisser road from Km 1-11 | Anantnag | 1955 | 2014-15 | 1444.4 | 90.56 | 100
110 | Widening / upgradation of Safapora Hakbara road | Bandipora | 610 | 2014-15 | 437.24 | 34.73 | 80
111 | Widening / upgradation of Nadihal Erin Bandipora road | Bandipora | 1057 | 2014-15 | 895.63 | 110.08 | 100
112 | Widening / upgradation of Chadoora Khanda road | Budgam | 1624 | 2014-15 | 844.84 | 178.75 | 99
113 | Upgradation of main road Marh Gangansoo from Sangrampora to Gangansoo Km 5-14 | Jammu | 1990 | 2014-15 | 1713.93 | 250.07 | 98
114 | Improvement / upgradation of road from Bantalab to Aghore upto double lane status road | Jammu | 1624 | 2014-15 | 963.4 | 224.05 | 94
115 | Construction of 445 mtr span double lane pre-stressed concrete bridge over river Ujh at Jothana | Kathua | 4554 | 2014-15 | 2206.94 | 162.87 | 60
116 | Improvement and upgradation of Hatli road from Km 7-18 (12 kms) | Kathua | 4052 | 2014-15 | 1083.71 | 173.49 | 52
117 | Const of road from Dangdoora to Hanzal (Marwah) Km 1-18 (Phase I) | Kishtwar | 3792 | 2014-15 | 0 | 0 | 0
118 | Construction / upgradation of Dhani Tadd upto Paradda Pandov including Surmapadi road | Kupwara | 1566 | 2014-15 | 414.28 | 242.84 | 82
119 | Construction / upgradation of Hafrada Astan Wali Hatchimarg Tumina Marsarai including Bulnad road | Kupwara | 1905 | 2014-15 | 810.04 | 209.5 | 87
120 | Widening / upgradation of Awantipora Tral road via Dadsara | Pulwama | 1430 | 2014-15 | 1178.97 | 99.42 | 100
121 | Widening / upgradation of Lassipora Arihal Khamri road | Pulwama | 692 | 2014-15 | 598.24 | 28.26 | 100
122 | Const of road from Kewal Morh to Targain via Gota Phase-I | Rajouri | 1586 | 2014-15 | 962.34 | 195.45 | 76
123 | Construction of road from Marasi Morh to Bagyal kote, High School Panchayatgarh Hubigala | Rajouri | 826 | 2014-15 | 740.49 | 84.51 | 95
124 | Improvement / upgradation of Samba Mansar road Km 11-19 | Samba | 2101 | 2014-15 | 2036.88 | 0 | 100
125 | Four lanning of Boulward road from Nehru Park to Kralsangri RD 2000-7000 | Srinagar | 3377 | 2014-15 | 234.99 | 300 | 100
126 | Upgradation of Khanabal Pahalgam road from Km 14.50 to Km 43 (Seer Hamdan to Pahalgam 28.50 km) (28.50 km) | Anantnag | 4886 | 2015-16 | 1890.23 | 671.88 | 82
127 | Upgradation of road from Sangam to Serigupwara via Khirim (25 km) | Anantnag | 4609 | 2015-16 | 2659.84 | 404.81 | 87
128 | Widening and upgradation of Gingal Bijhama Lachipora road upto Muqam / Mayen (16 km) | Baramulla | 2119 | 2015-16 | 1075.23 | 232.66 | 82
129 | Upgradation of Hygam Tarzoo Sopore road (15 km) | Baramulla | 1415 | 2015-16 | 554.57 | 0 | 77
130 | Widening / upgradation of Ladoora Achabal road (10 km) | Baramulla | 1711 | 2015-16 | 801.45 | 257.89 | 100
131 | Upgradation of Sopore Shiva road including allied links of Duroo & Hars Shiva | Baramulla | 1765 | 2015-16 | 461.98 | 0 | 44
132 | Upgradation of Magam Beeru Budgam road | Budgam | 3185 | 2015-16 | 2268.49 | 411.88 | 97
133 | Const of 2000 m span double lane pre-stressed bridge over river Chenab at Indirpatian Pargwal | Jammu | 20690 | 2015-16 | 1551.04 | 391.27 | 40
134 | Improvement / widening (double laning) of Lakhanpur Thein road upto Ranjit Sagar dam (19 km) | Kathua | 4349 | 2015-16 | 1957.28 | 13.03 | 70
135 | Improvement / upgradation of Khumiriyal rang road (25 km) | Kupwara | 3038 | 2015-16 | 449.85 | 0 | 35
136 | Improvement and upgradation of Koteranka Khawas road Km 1 to 30.20 (30 km) | Rajouri | 7620 | 2015-16 | 1366.68 | 500 | 50
137 | Const of 80 m span pre stressed concrete bridge over Sukh Tawi nalla from Vedant Ashram to MES store with approach road | Rajouri | 662 | 2015-16 | 524.68 | 137.32 | 87
138 | Const of 160 m (4x40) pre stressed concrete girder motorable bridge over Rajouri Tawi to Panjpeer Badala Mang at Rajouri | Rajouri | 1680 | 2015-16 | 542.76 | 0 | 32
139 | Widening / upgradation of Bijbehara Shopian road (12 kms) | Shopian | 4893 | 2015-16 | 1286.87 | 0 | 51
140 | Improvement / upgradation of road from Zero bridge to IG road (10.50 km) | Srinagar | 2879 | 2015-16 | 1279.77 | 173.59 | 82
141 | Upgrdation of road from Thail to Chountra Mata in Km 6th RD 500 to Km 19th RD 500 ( 13 km) | Udhampur | 2520 | 2015-16 | 445.02 | 0 | 35
142 | Const of 4x33 mtr plate girder bridge on ADV road Km 9th at Larkipora | Anantnag | 1250 | 2016-17 | 265.37 | 399.23 | 95
143 | Construction of bridge at river Jehlum at Gadihanjipora, Bijbehara | Anantnag | 1200 | 2016-17 | 310.93 | 0 | 26
144 | Const. of 2x25 Mtr span bridge at Rakhi Chee | Anantnag | 354.57 | 2016-17 | 322.08 | 0 | 100
145 | Upgradation of Mattan Akura Poshkeri road upto Hugam Nambal | Anantnag | 2000 | 2016-17 | 619.76 | 0 | 62
146 | Construction of 2x45 Mtr Trussed Girder Bridge at Rein Chowgund Road over Nallah Sundran | Anantnag | 940.44 | 2016-17 | 270.21 | 204.37 | 85
147 | Verinag-Karpran road | Anantnag | 1500 | 2016-17 | 381.55 | 0 | 70
148 | Construction of road along old Brengi Canal | Anantnag | 1500 | 2016-17 | 378.55 | 0 | 63
149 | Upgradation of Seer Hapatnar Ashamgam road | Anantnag | 2000 | 2016-17 | 584.94 | 541.71 | 80
150 | Improvement/ Upgradation of Brakpora-Kanganhal-Chattergul road | Anantnag | 2000 | 2016-17 | 933.19 | 407.27 | 82
151 | Upgradation of Mattan Achabal road | Anantnag | 1000 | 2016-17 | 592.16 | 167.58 | 90
152 | Const of 4x25 m span plate girder bridge on Nallah Arin connecting Arin and Babapora incld const of approach road | Bandipora | 789.94 | 2016-17 | 433.12 | 112.6 | 91
153 | Const of 5x40 Mtr span (200 Mtr long) Steel Girder bridge over Nallah Ferozpura at Nowgam Zalpora | Bandipora | 1137.21 | 2016-17 | 757.92 | 270.33 | 95
154 | Srinagar Bandipora road | Bandipora | 1849.3 | 2016-17 | 1328.05 | 363.18 | 100
155 | Const of Wanpora Markoot road via Peerbaaba Dawar Kishanganga right abutment | Bandipora | 1000 | 2016-17 | 48.65 | 0 | 27
156 | Upgradation / widening of Choora - Burzbashan - Dardpora Tilgam road including Athoora- Hail, Bulgam link | Baramulla | 1500 | 2016-17 | 738.63 | 436.36 | 93
157 | 3x15 mtr span bridge Gurseer - Gagir over river Jehlum | Baramulla | 1500 | 2016-17 | 81.49 | 0 | 15
158 | Widening / upgrad of Zehanpora Shahdara Sharief road | Baramulla | 2000 | 2016-17 | 896.6 | 244.36 | 82
159 | Widening/ upgradation of Watlab Chetkak road | Baramulla | 1400 | 2016-17 | 181.94 | 0 | 25
160 | Construction of 1x20 Mtr Twin Foot Bridges over Nallah Doodganga at Kherigund Chadoora | Budgam | 242.47 | 2016-17 | 77.12 | 0 | 55
161 | Upgradation of Chadoora- Branwar road upto Haijan | Budgam | 1500 | 2016-17 | 302.2 | 336.76 | 86
162 | Upgradation of road from Randak Daji Jawalpora Waterihal Gaffar Abad via Samsen upto Yarikhah | Budgam | 1500 | 2016-17 | 691.85 | 530.26 | 100
163 | Upgradation of road from Aripanthan to Khag | Budgam | 1308.5 | 2016-17 | 404.82 | 0 | 77
164 | Construction of link road from Chilly Pain to KuttiKulth va Muksyas Chilly Bala | Doda | 1200 | 2016-17 | 176.26 | 0 | 30
165 | Construction of road from Pul Doda to Deoli via Doda town | Doda | 1500 | 2016-17 | 8 | 322.5 | 52
166 | Construction of road from Bhatya to Challar via Jakyas | Doda | 1000 | 2016-17 | 83.93 | 0 | 25
167 | 4 lanning of Pandach - Beehama road | Ganderbal | 2000 | 2016-17 | 201.26 | 0 | 31
168 | Sumbal Bala road | Ganderbal | 748 | 2016-17 | 86.17 | 0 | 23
169 | Construction of road from Bamyal to Deva Mai Temple via Holy Mandir including 45 m span bridge over Holy Nallah | Jammu | 1500 | 2016-17 | 428.91 | 280.14 | 70
170 | Widening/ upgradation of RS Pura Suchetgarh road up to 4 laning km 1 to 7 RD 800 | Jammu | 1500 | 2016-17 | 162.73 | 0 | 58
171 | Construction of balance work of 220 m span motorable bridge over Nalla Ujh near Guddu Flail | Kathua | 1000 | 2016-17 | 679.25 | 158.25 | 85
172 | Improvement/ widening of old Samba-Kathua road | Kathua | 1500 | 2016-17 | 410.13 | 9.77 | 65
173 | Construction / Upgradation / widening of road from Dayalachak to Kattal Gujjara Length 12.0 kms | Kathua | 1000 | 2016-17 | 675.38 | 153.62 | 90
174 | Improvement/ upgradation of HastiSarthal Devi ji road km 1st to 20th | Kishtwar | 2000 | 2016-17 | 522.19 | 245.68 | 55
175 | Improvement/ upgradatopm of road from Bhaderkote to Dangdooru | Kishtwar | 1200 | 2016-17 | 561.36 | 436.76 | 82
176 | Strengthening /upgradation of Buygam Nani Bugh Srendoo Ashmuji, Bogund Supar and Kanipora road | Kulgam | 1061 | 2016-17 | 450.89 | 167.85 | 90
177 | Const of 3X40 Mtr span Grider bridge on Chalan Asthal road at village Asthal | Kulgam | 955 | 2016-17 | 584.72 | 141.23 | 99
178 | Adjan Bridge at Kulgam | Kulgam | 2000 | 2016-17 | 469.17 | 0 | 61
179 | Upgradation of Vilgam, Champora, Hafrad road including Dohama and Tarathpora road | Kupwara | 1500 | 2016-17 | 648.45 | 358.36 | 100
180 | Construction of road from Tangdar to Gabra via Hajitra | Kupwara | 1581.5 | 2016-17 | 315.82 | 443.55 | 85
181 | Upgradation of Salkoot Halmatpora Batergam Gushi including Marhana Daribal road viz Ziyarat Sharif | Kupwara | 1500 | 2016-17 | 975.42 | 98.67 | 90
182 | Widening / upgrad of Chontipora to Darbal via Batagund / Wajhama | Kupwara | 1500 | 2016-17 | 511.34 | 191.55 | 82
183 | Const of Khumriyal Shumriytal Gund Jahangir road incld Doniwari Kantpora and Sewar Kawari road | Kupwara | 1500 | 2016-17 | 739.78 | 330.51 | 95
184 | Const of Handwara –Bangus road (Phase-I) | Kupwara | 2000 | 2016-17 | 807.39 | 0 | 70
185 | Construction of 110 m span double lane pre-stressed concrete motorable bridge with 1.2 m wide walk way on both sides over Mandi Nallah at Mandi | Poonch | 1125.1 | 2016-17 | 365.18 | 0 | 36
186 | Construction of 140 m (4x35m) span double lane pre-streessed concrete motorable bridge with 1.2 m wide walk way on both sides over Mendhar Nallah at Mankote | Poonch | 1109.9 | 2016-17 | 899.45 | 0 | 95
187 | Strengthening/ Widening/ Upgradation of road from National Highway 44 (LPD Bottling Plant) to Andrasoo via Gas Turbine-Konibal | Pulwama | 1188.7 | 2016-17 | 561.9 | 116.61 | 99
188 | Below Drabgam Shadimarg road | Pulwama | 927.59 | 2016-17 | 610.8 | 157.08 | 100
189 | Drabgam-C.B Nathachgoze road | Pulwama | 1170 | 2016-17 | 668.13 | 104.04 | 94
190 | Tral to Satoora and Khankah to Pastoona via Batgund including bridge (Phase-I) | Pulwama | 1500 | 2016-17 | 345.27 | 0 | 88
191 | Upgradation of Devak Hathal road in Rajouri district constituency Nowshera district Rajouri (L=24 kms) | Rajouri | 1500 | 2016-17 | 741.2 | 78.18 | 75
192 | Construction of 32 m span double lane bridge at Rajouri (Hamilton) including approaches | Rajouri | 540 | 2016-17 | 230.15 | 9.77 | 65
193 | Construction of 80 m span steel girder motorable bridge including approaches at Dharat Dhandani | Rajouri | 440 | 2016-17 | 196.49 | 42.35 | 60
194 | Construction of road from Khari Kote to Sarachi, Sub-division Ramsoo | Ramban | 1200 | 2016-17 | 14.78 | 0 | 15
195 | Construction of 160 m span pre-stressed RCC double lane bridge at the take-off point at Jhajjar on Panthal Jhajjar road | Reasi | 2000 | 2016-17 | 178.26 | 0 | 45
196 | Widening/ upgradation of Panthal Jhajjar road from Km 1st to 13th | Reasi | 1700 | 2016-17 | 343.86 | 0 | 45
197 | Impovement/ upgradation of road from Narloo to Hunder Gali (Hospital) | Reasi | 1700 | 2016-17 | 427.12 | 0 | 35
198 | Improvement/ upgradation of road from railway station to Nangal including construction of 60 m bridge. | Reasi | 1500 | 2016-17 | 354.82 | 210.35 | 55
199 | Construction of road from Tuli to Dharmari via Banna/ Thiloo | Reasi | 1000 | 2016-17 | 55.5 | 0 | 15
200 | Construction of bridge at Utterbani over river Devak at village Utterbani in Samba Constituency | Samba | 1200 | 2016-17 | 450.5 | 123.78 | 65
201 | Improvement/ upgradation/ strengthening of Samba Sumb road | Samba | 1800 | 2016-17 | 635.72 | 425 | 61
202 | Widening/ improvement of Utterbebani Purmandal road via Mandal | Samba | 1800 | 2016-17 | 1420.73 | 379.27 | 100
203 | Approach road and underpass for AIIMS at Vijaypur | Samba | 1988 | 2016-17 | 491.37 | 65.15 | 50
204 | Widening of existing Raya Morh,Raya Suchani Mandal link road (Central University road double lane) | Samba | 2000 | 2016-17 | 667.48 | 358.32 | 65
205 | Upgradation of Nagbal Turkawangam road and Wasohallan Hajipora road including Baskuchan Kahwara road. | Shopian | 246.45 | 2016-17 | 81.92 | 0 | 55
206 | 230 mtr span second bridge over river Jhelum Near Doordarshan Kendra Connecting Rajbagh with TRC alongwith Viaduct span | Srinagar | 3200 | 2016-17 | 0 | 0 | 0
207 | Upgradation of Udhampur Ghordi road from single lane to double lane | Udhampur | 4000 | 2016-17 | 336.05 | 651.5 | 51
208 | Construction of Mantali Dudu Road | Udhampur | 1000 | 2016-17 | 373.16 | 16.29 | 51
209 | Construction of road from Ramnagar to Chatredi (Phase-I) | Udhampur | 1000 | 2016-17 | 232.29 | 0 | 38
210 | Additional 30 m span RCC bridge over river Jehlum at Khanabal | Anantnag | 1746 | 2017-18 | 35.19 | 0 | 16
211 | Widening / upgradation of Pahalgam Aroo road | Anantnag | 1312 | 2017-18 | 17.73 | 0 | 16
212 | Const / upgrad of Bindoo Damdulow via Bidder to Tantrapora Zambalgam Veerinag | Anantnag | 1452 | 2017-18 | 42.72 | 0 | 26
213 | Upgrad of Kadipora Gopalpora via Feth Grah University upto Tailwani Shangus | Anantnag | 1753 | 2017-18 | 154.67 | 0 | 20
214 | Restoration / upgradation of Sumbal Bandipora road from Ajas Sonarwani | Bandipora | 2333 | 2017-18 | 419.83 | 0 | 46
215 | Impvt / upgrad of Athwatoo Bunkote Sonawari road | Bandipora | 1479 | 2017-18 | 138.36 | 0 | 35
216 | Widening / upgradation of Rawoocha Pazalpora Hama Markote road | Baramulla | 1120 | 2017-18 | 39.65 | 0 | 8
217 | Upgrad of Kansipora Kandi road via Singhpora incld Delina Katianwali and allied links | Baramulla | 1153 | 2017-18 | 56.03 | 0 | 20
218 | Widening / upgradation of Hyderbeg to Chanderseer road, Boch to Shatabugh road and Takiya tapper to Check Tapper road Phase-l | Baramulla | 1985 | 2017-18 | 108.03 | 0 | 30
219 | Upgradation /widening of Rohama Brandub Road | Baramulla | 1185 | 2017-18 | 26.84 | 0 | 8
220 | Sheeri Heewan Laridora Sultanpora road | Baramulla | 1200 | 2017-18 | 136.91 | 0 | 30
221 | Upgradation of Razwat Wagub Amargrah krankshivan and Seer road incld inner tinks | Baramulla | 1393 | 2017-18 | 8.26 | 0 | 3
222 | Widening/upgradation of Sopore Harwan road incI inner tinks of Brath Tujjar Nowpora and Latishart | Baramulla | 878 | 2017-18 | 33.7 | 0 | 32
223 | Upgradation of road from Chechitora Goigam pinjoorab to chanditoora | Baramulla | 1796 | 2017-18 | 46.13 | 0 | 15
224 | Widening/ upgradation of Zainpora Shadra road Phase ll (Paramptia to Shadra) | Baramulla | 2586 | 2017-18 | 0 | 0 | 2
225 | Upgradation from Dobiwan to Zandpal via Hardaboora, Checkfrestershi, Kharpora Naidcheck Phase lst | Baramulla | 1049 | 2017-18 | 19.03 | 0 | 10
226 | Construction of link road from Dhamunda morh to Jai via Manthla, Kakol | Doda | 1493 | 2017-18 | 2.5 | 0 | 0
227 | Construction of link road from Sikku to Jagota take of from Chiralla road km 7th RD 725 | Doda | 1976 | 2017-18 | 0 | 0 | 0
228 | Const of link road from Tanta to Draman via Kunthal | Doda | 800 | 2017-18 | 0 | 0 | 5
229 | Const of link road from Gai Dessa to Bhatta via Mangalthatha and Dewalkumd | Doda | 700 | 2017-18 | 18 | 0 | 10
230 | Const of road from Humbal to Dedni | Doda | 1427 | 2017-18 | 48 | 0 | 40
231 | Const of 125 m single lane steel girder through type motorable bridge over river Chenab at Sui Gwari connecting Jodhpur | Doda | 1796 | 2017-18 | 286.05 | 360.27 | 65
232 | Const of bridge over river Chenab at Marsoo (Assar) | Doda | 2000 | 2017-18 | 61 | 0 | 20
233 | Construction of Urlani to Pali bridge | Jammu | 800 | 2017-18 | 121 | 94.47 | 52
234 | Jhajjar Kotli to Badsoo connecting Dansal via Shaddali | Jammu | 1500 | 2017-18 | 97.1 | 0 | 10
235 | Kotli Matwar road and link road Mawa to Talli Ghai | Jammu | 1153 | 2017-18 | 114.4 | 254.08 | 52
236 | Improvement / upgradation of road from R S Pura to Saleher via Check-i-Islam | Jammu | 1400 | 2017-18 | 8 | 0 | 20
237 | Const of 200 m span doule lane prestressed cement bridge over Manwar on Baldoh to Thakkar road in block Khour | Jammu | 1500 | 2017-18 | 66.47 | 0 | 19
238 | Widening / upgradation of road from Marh to Baba Talab via Jaffra Chak and to Halqa via Hira Chak Makyala upto Gadala and allied links upto Kana Chak in Block Marh | Jammu | 1995 | 2017-18 | 247.15 | 0 | 18
239 | Const of 250 m double lane bridge over Nallah Aik connecting Sai Fagla Mule Check in Suchetghar | Jammu | 2575 | 2017-18 | 690 | 456.04 | 72
240 | Bani to Billawar via Dagger (L=5.00 km) | Kathua | 2000 | 2017-18 | 51 | 0 | 3
241 | Upgradation of Sukrala road (double lane specifications) (L=6.00 km) | Kathua | 1800 | 2017-18 | 622.17 | 582.99 | 93
242 | Chadwal to Magloor via Mouri (L=7.00 km) | Kathua | 2000 | 2017-18 | 294.01 | 925.16 | 80
243 | Const of bridge over Sugal Khad on Manu Hatli roads | Kathua | 1075 | 2017-18 | 0 | 0 | 0
244 | Const of road from Galman to Dasanoo via Kohli Kopper | Kathua | 1000 | 2017-18 | 31.07 | 0 | 16
245 | Const of bridge over Nallah Behani at Niali | Kathua | 1350 | 2017-18 | 0 | 0 | 0
246 | Const of bridge over river Sewa near Mela ground at Bani linking Dhaggar to Bani Bhaderwah | Kathua | 560 | 2017-18 | 0 | 0 | 0
247 | Widening of Pinther to Billawar road alongwith balance work of Billawar to Sukrala road | Kathua | 2362 | 2017-18 | 191 | 0 | 40
248 | Const of link road from Padyarna to Pullar from Km 3rd to 12 Nagseni | Kishtwar | 1475 | 2017-18 | 0 | 0 | 7
249 | Upgradation of Khudwani Nawbal Arwani road incld interior road | Kulgam | 1418 | 2017-18 | 10.17 | 0 | 19
250 | Widening / upgradation of Munand Atamgung Daderkote Tsenskar Kutgam | Kulgam | 2093 | 2017-18 | 311.28 | 0 | 34
251 | Widening / upgradation of Levdoora to Y K Pora Nagrass Pir Takiya Botiangoo incld Razloo Chittergam Kund road | Kulgam | 1353 | 2017-18 | 98.02 | 0 | 29
252 | Construction of Handwara Bangus road stage 2nd | Kupwara | 2859 | 2017-18 | 0 | 0 | 1
253 | Construction / upgradation of Jami Masjid Kandi Tandar road via Vittage Jada 14 km | Kupwara | 1114 | 2017-18 | 92.28 | 0 | 5
254 | Widening / upgradation of Thokerpora Pazatpora Ganapora road inctuding allied links | Kupwara | 1238 | 2017-18 | 361.73 | 287.53 | 80
255 | Construction / upgradation of Nagsari A&B Nari Koti and Ladda road at Kalrooch Lolab Kupwara phase I | Kupwara | 849 | 2017-18 | 57.5 | 0 | 30
256 | Batergrm via Kanari Trehgam Dootipora Hayen Hundi Kawari Heri Zorhama Abura Reshwari in Kupwara | Kupwara | 1469 | 2017-18 | 85.92 | 0 | 30
257 | Construction of 65m & 80 m span prestressesd concrete motorabte bridge with 1.2m wide watk way on both side over Mendhari Natta including approaches, corss drainage and protection works on upstream/ downstream on Mendhar town | Poonch | 1340 | 2017-18 | 40 | 0 | 55
258 | Impvt / upgrad of road from Chandak Budha Amarnath | Poonch | 1166 | 2017-18 | 180 | 0 | 45
259 | Const of road from Bedar to Brachar via Chamber | Poonch | 1390 | 2017-18 | 24 | 0 | 15
260 | Widening / strenthening of Tahab Chakura Naina Chakura Malangpora road | Pulwama | 1016 | 2017-18 | 161.82 | 0 | 58
261 | Widening upgradation Pulwama Rahmoo road including Pulwama Rajpora Shadimarg road | Pulwama | 1600 | 2017-18 | 83.97 | 0 | 50
262 | Road from Gulhati to Shahdara Sharief via Ladyal Moriyan and Ghambir Gali | Rajouri | 1700 | 2017-18 | 39.5 | 0 | 22
263 | Const of 60 m span Nonial Manpur birdge at Nowshera | Rajouri | 550 | 2017-18 | 20 | 0 | 32
264 | Const of 50 m span motorable span motorable bridge at Dhaleri over Dhaleri Nallah in Darhal | Rajouri | 400 | 2017-18 | 2 | 0 | 5
265 | Const of 100 m span motorable bridge including approach road over Nowshera tawi | Rajouri | 1600 | 2017-18 | 8 | 0 | 15
266 | Road from Kha to Kharian | Rajouri | 1800 | 2017-18 | 0 | 0 | 0
267 | 2 lane bridge over river Chenab | Ramban | 4100 | 2017-18 | 0 | 0 | 0
268 | Construction of 202 mtr span Prestressed concrete motorable bridge double lane with foot path over River Chenab at Ramban | Ramban | 4178 | 2017-18 | 0 | 0 | 2
269 | Construction of road from Jij to Narkote via Chakalwala | Reasi | 1850 | 2017-18 | 0 | 0 | 0
270 | Const/ upgradation of Samba Sumb Goran road Km 11 to 20 double lane | Samba | 1200 | 2017-18 | 253.25 | 0 | 36
271 | Upgrad of road from Baba Chamail to NH via Baba Sidh Goria Swankha | Samba | 800 | 2017-18 | 8.5 | 0 | 5
272 | Impvt / upgrad of road Vijayur Ramgarh to SM pura (double lane) | Samba | 1800 | 2017-18 | 358.82 | 130.3 | 52
273 | Const / upgrad of road from Shah Balode to Utterbani via Sarna Chilla Danga and lovely Km 11 to 20 | Samba | 900 | 2017-18 | 63.5 | 0 | 12
274 | Widening / upgradation of Zainpora Khujipora road via Hydergund incld Shermal Zainapora link road | Shopian | 2120 | 2017-18 | 86.77 | 0 | 20
275 | Construction of road from Dobzan to Chanch Marg road Shopian Phase I | Shopian | 1471 | 2017-18 | 0 | 0 | 1
276 | Improvement and upgradation of Shalla Naseem road from Zakoora crossing to Shalimar Chowk | Srinagar | 871 | 2017-18 | 0 | 0 | 8
277 | Const of road from Pantha Chowk to Khonmoh Zawoora to Sempora | Srinagar | 1398 | 2017-18 | 0 | 0 | 5
278 | Ramnagar to Basantgarh (Ph -II) | Udhampur | 1800 | 2017-18 | 0 | 0 | 2
279 | Malsar to Latijar via Shalala | Doda | 1206 | 2018-19 | 17 | 0 | 10
280 | Chattargalla to Kalaish Kund | Doda | 1900 | 2018-19 | 0 | 0 | 0
281 | Padhari to Bhal Padhari | Doda | 1900 | 2018-19 | 0 | 0 | 0
282 | Jai to Suranga Morh | Doda | 1700 | 2018-19 | 26 | 0 | 25
283 | Goilbar to Benencha | Doda | 1300 | 2018-19 | 26 | 138.42 | 55
284 | Const of road from Barshalla to Bhalwana via Sisool | Doda | 1800 | 2018-19 | 0 | 0 | 3
285 | Construction of link road from Malsar to Shalala Dherwari Latizar | Doda | 998 | 2018-19 | 0 | 0 | 0
286 | Upgradation and widening of road link from RCC bridge Bhambaran to Daskai via Akhnoor Bus Stand and to Pannu chowk and alllied link | Jammu | 2000 | 2018-19 | 8 | 0 | 16
287 | Construction of link road from HSDJi road km 12th to Hasti Zig on NH-244 via Drab, Takna, Mandri & Butpora | Kishtwar | 2426 | 2018-19 | 0 | 0 | 22
288 | Construction of bypass road taking off from NH-1B road at Dewaroo Kishtwar to Dugga Kishtwar connecting to Kishtwar Synthan NH 1B road Phase 1 upot single status | Kishtwar | 1896 | 2018-19 | 2 | 0 | 30
289 | Construction of road from tagood Baddevna including link to village karoor | Kishtwar | 2000 | 2018-19 | 0 | 0 | 5
290 | Chaura Gali to Ladote via Muku Brada | Rajouri | 1500 | 2018-19 | 13 | 0 | 10
291 | Bhanjwal Peli Border road | Rajouri | 2100 | 2018-19 | 0 | 0 | 18
292 | Devak Bhambliya road connecting Sanki Deoli Hathal Saroti Nowshera | Rajouri | 2000 | 2018-19 | 0 | 0 | 25
293 | Const of Kanda to Ransoo road | Reasi | 1886 | 2018-19 | 0 | 0 | 22